## Sheet1
|  |  | The white and gray cell backgrounds are only for ease of visual distinction. | [6 empty] | Risk Product = RP | RP > 12 | HIGH
|  |  | OsCorp Risk Register | [7 empty] | 4 > RQ ≤ 12 | MODERATE
[11 empty] | RQ ≤ 4 | LOW
ID Code | Name | Category | Risk Description | Opportunity/Threat | Current Controls | Risk Response | Risk Strategy | Probability | Impact | Risk Product | Owner
This risk ID code allows the Team to uniquely identify each risk. | This name allows each Team member to easily understand and uniquely identify the essence of the risk. | This category explains the risk's root cause(s) - Physical, Technical, Social, Process, or/and Third Party. Each risk must have at least 1 root cause. | This risk description gives a brief explanation of the risk. | By default, each risk is assumed to be a problem. Positive risks (opportunities) are not cataloged here. | What controls, if any, exist to reduce the probability or/and impact of this risk? | Actions for the risk owner to take so the risk owner is may successfully handle the risk. | How should the risk owner handle this risk (Avoid, Mitigate, Transfer, or Accept)? | Chance of risk occurring. 0 = never, 5 = definite. | A value between 1 (low) and 5 (high) to describe the weight of this risk. | Risk Product (RP) = Probability * Impact | The risk owner is the person in charge of addressing this risk, and is responsible for the results of his/her response.
1 | Physical Security Breach | Physical | Someone breaks into the facility or otherwise causes physical harm to servers or significant company property. | Threat | Security cameras, electronic locks, 24/7 monitoring of physical facilities. Physical security is OsCorp's specialty! | Call law enforcement. Keep notes on physical vulnerabilities. Screen candidates before entry for suspected threats. | Accept | 1 | 3 | 3 | Douglas Leach
2 | Ransomware: Encrypting Company Data | Technical | Company or customer data becomes encrypted due to a ransomware attack. | Threat | Company and customer data are backed up off-site periodically, and these backups are also checked periodically. | Call law enforcement. Keep daily backups of data in a secure off-site location. | Mitigate | 3 | 4 | 12 | Douglas Leach
3 | Phishing Attack Success | Technical, Social | A malicious entity baits someone in the company (probably via email) into disclosing unauthorized details, such as user names, passwords, social security numbers, customer data, or other matters meant to remain secure. | Threat | All employees must undergo a basic web and cybersecurity training module as part of onboarding. | Call law enforcement depending on the severity of the attack. Upgrade the current training to phishing simulations on a periodic basis (once or twice a year), ensuring only some employees are in training at any one time to reduce suspicion. | Mitigate | 4 | 4 | 16 | Niel Bogart
4 | Third Party Contract & Risk Assessment | Third Party | OsCorp may use unsecure or suspicious third party vendors for its cybersecurity and IT products and services. | Threat | Third party IT/cybersecurity contracts are reviewed in-house by procurement and finance professionals, not IT. | Involve experienced members of IT/cybersecurity teams in contract review and interviewing third party vendors. Check for NIST and ISO 27001 compliance from reputable sources. Have IT/cybersecurity interview third parties before signing. | Mitigate | 2 | 3 | 6 | Greg Campbell
5 | Principle of Least Privilege | Process | A lack of company-wide policy enforcing the principle of least privilege means users can unintentionally access more content and administrative options than intended, possibly causing data loss or data leaks. Hackers could easily exploit overprivileged accounts if they knew this system existed. | Threat | OsCorp uses Microsoft Active Directory to manage accounts, but there is no account access management in place for admin or privileged accounts. | Use privileged account access management software. Develop and enforce relevant policies and procedures regarding the principle of least privilege. | Mitigate | 3 | 4 | 12 | Hector Gonzalez
6 | Multifactor Authentication (MFA) | Technical, Process | Logging into company systems requires multifactor authentication with a code sent to a user's authenticator or phone app. | Threat | OsCorp uses Microsoft Active Directory, but does not enforce multifactor authentication for login to all its systems. | Implement and require multifactor authentication for all company systems. | Mitigate | 5 | 3 | 15 | Jeff Wind
7 | Defense in Depth (DID) | Technical, Process | Network security should have multiple firewalls and security devices in sequence from varying trusted vendors to deter hackers. | Threat | OsCorp uses Palo Alto Next Generation Firewalls (NGFW), but only as a single layer of defense. | Add layers of defense by adding different next generation firewalls from different vendors behind the Palo Alto ones. | Mitigate | 3 | 4 | 12 | Joseph Mahler
8 | Data Loss Prevention (DLP) | Technical, Process | OsCorp should have systems that detect and prevent critical or unauthorized data from being copied to removable media (flash drives, DVDs, etc.) as well as from being sent outside the network. OsCorp also needs to catalog data based on criticality. | Threat | Data is stored on Microsoft Azure's public cloud which has a configurable DLP. It has not been properly configured since data has not been properly categorized. | Configure the built-in DLP by categorizing data and ensure the DLP is properly configured. | Mitigate | 3 | 5 | 15 | Joseph Mahler
9 | General IT/Cybersecurity Policy | Process | Best practice is to have and consistently enforce a company-wide policy for IT and cybersecurity, including an acceptable use policy (AUP). Not doing this is asking for trouble via misused devices or software. | Threat | OsCorp has experienced professions who have often played fast and loose with word-of-mouth preferences on how things should be handled. There is no definite AUP in place. | Develop and enforce an acceptable use policy company-wide. Update it as prudent. | Mitigate | 5 | 2 | 10 | Joseph Mahler
10 | Security Information and Event Management (SIEM) | Technical | A SIEM combines, analyzes, and correlates log data with alerts in real time. It must be configured and personnel must be trained to use it. | Threat | The IT team periodically reviews logs from Microsoft Antivirus and responses from white hack hackers who volunteered to test the public website for free. There is no formal SIEM nor trained team in place. | Investigate on-site and third-party SIEM options as budget allows. A SIEM and trained personnel - even contracted out - would likely be a major expense, and may be too much for a company of about 50 people. | Mitigate | 4 | 3 | 12 | Greg Campbell
11 | Internal Cybersecurity Risk Management | Process, Social, Technical | There is a significant chance the C-suite or/and technical teams would be overwhelmed by all the recommendations available for cybersecurity things to fix or improve. | Threat | OsCorp has a team to handle financial risks, not technical ones. There is no known GRC involvement aside from me. | Conduct penetration tests on all relevant devices. Determine system vulnerabilities. Compile a categorized spreadsheet by sensitivity and criticality of all assets. Ensure someone who understands the risks also quantifies them by impact and likelihood. | Mitigate | 4 | 3 | 12 | Ryan Shane
12 | Vulnerability Management | Technical, Process | Best practice is to have a set schedule to identify and categorize the type and severity level of all software, hardware, and firmware vulnerabilities in a OsCorp. Not doing this is asking for trouble via hackers. | Threat | OsCorp uses the latest publicly available security updates for hardware, software, and firmware without testing them first. OsCorp also has Qualys, which they periodically use to identify and fix vulnerabilities. | Run Qualys and perhaps other vulnerability scanners during times when most employees are on-site or otherwise running work devices for maximum vulnerability detectability. Investigate output messages to determine what is vulnerable, how severe it is, and what would be involved in fixing it, noting there may be false positives, duplicate entries, or things outside the organization's immediate budget or plan to fix. Develop and enforce a policy to do periodic vulnerability scans of the entire system. | Mitigate | 3 | 4 | 12 | Joseph Mahler
13 | Business Continuity/Disaster Recovery | Process | A natural disaster like a flood or meteor could wipe out OsCorp. | Threat | Most of OsCorp's data is in major cloud providers like Microsoft, and OsCorp uses various softwares-as-a-service (SaaS). Cloud data backups are done and tested periodically. There is a clearly documented business continuity plan. This is another strength of OsCorp. | Disaster and disaster recovery simulation exercises are useful to do periodically. | Accept | 2 | 1 | 2 | Greg Campbell
14 | Asset Management | Technical, Process | Periodically identify, categorize, and update company assets (hardware, software, intellectual property/IP, and key personnel) in an internal asset register spreadsheet. Each entry should have at least the columns of unique ID, an owner, a description, a criticality score (necessary for business operations), a sensitivity score (necessary for adhering to privacy laws), and a physical or digital location depending on what it is, like Jeff's PC in Room 327 or Network 529EE or the Jerusalem office. (You can only purposely defend or act upon what you know exists.) | Threat | OsCorp does network scans of devices and cataloged in a spreadsheet all the serial numbers of the laptops they have, including their model numbers and warranty info. | Instead of not knowing what OsCorp has, even with its 50ish member organization, have someone thoroughly catalog OsCorp's assets into an asset register as previously described. | Mitigate | 3 | 3 | 9 | Joseph Mahler